## Burn Down Chart
Project Title: IOT Smart Fan Release #: 1.0 Sprint #:1
| User Story ID | User Story | Tasks | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| 1 | As a member I would like to Create Sprint Product log | create a sprint product log | Mark Piland | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 2 | As a member I would like to Create Sprint Burn down chart | Create a spring burndown chart | Mark Piland | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 3 | As a member I would like to Create Sprint back log | Create spring back log | Mark Piland | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 4 | As a member I would like to Identify IOT application | Identify IOT application | Mark Piland | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 5 | As a member I would like toIdentify the IOT embedded device to be use | identify IOT embedded device that is to be used | Mark Piland | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 6 | As a member I would like to create a deployment strategy | Create a deployment strategy | Mark Piland | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 7 | As a member I would like to create a draft UML case diagram for a IOT device and the user end | Create a UML case diagram | Mark Piland | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 8 | As a member I would like to create a UML component diagram | Create a UML component diagram | Mark Piland | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 9 | As a member I would like to create a class diagram modeling the attributes for the IoT device | Create a class diagram | Mark Piland | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 10 | As a member I would like to create a UML deployment diagram | Create a UML deployment | Mark Piland | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 11 | As a member I would like to create a design report | Create a design report | Mark Piland | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 11 | 10.2 | 9.4 | 8.6 | 7.8 | 7 | 6.2 | 5.4
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 11 | 11 | 11 | 11 | 11 | 11 | 0 | 0

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints).
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log.
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C.
Step 4 | Break the User Story into a series of step by step development tasks in Column D.
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories.
Step 6 | Assign the User Story to a single team member in Column E.
Step 7 | Repeat Steps 4-6 for each User Story that has been planned for this Sprint.
Step 8 | At the end of each day, each team member should update the effort hours that were worked on their User Story to burn their work down.
Step 9 | After each Daily Standup, each team member should review the Burn Down Chart to ensure your Sprint will be delivered on time.